DRAFT Clallam County Emergency Management Communications Planning Tool

Actions for COML:

- Staff Comm Unit

  - Open ICS 214 Unit Log for Communications Unit.

  - Establish Message Center.

  - Review ICS 204 Assignment List for necessary skills and assign resources to positions based on task priority and skill base. Start ICS 210 resource status change form (update ICS 210 as resources arrive and manpower is reassigned to increase coverage.

- Begin ICS 217 Radio Frequency Assignment sheet. Refer to Appendices A-X ( Clallam County IS 205, Field Interoperability Guides: NIFOG, AUXFOG, WA SCIP, WAESF2 Appendix1 etc.) attached.

    - Develop a situational awareness as to Comms requirements. Debrief with IC/Operations & Sit/Stat etc.

    - What is working/not working? Monitor & conduct tests of primary comms. (IAW SOPs).

    - What are the Command communications priorities? Request ICS 312 from Command (provide recommended priorities if requested, d.& e. below should be 1&2).

- Establish Communications, Command & Control capability with Field Commanders, Area Commands, ICP’s and Up Chain to WADEM, WA Nat’l Guard & FEMA etc. Refer to Appendices A-X (Field Interoperability Guides: NIFOG, AUXFOG, WA SCIP, WAESF2 Appendix1 etc.) attached.

  - Establish communications channels for First Responders. Refer to ICS205, WA SCIP and NIFOG as appropriate for each entity.  In absence of Dispatch (Pencom, WSP etc.), establish nets for each as appropriate and resources allow.

    - Law Enforcement (recommend establishing area nets using existing frequencies & areas)

    - Fire (recommend establishing District nets using existing frequencies and district boundaries, augment with ARES as available)

    - Medical (recommend using fire EMS nets as above, augment with ARES as available)

    - SAR (recommend SAR 155.16 mhz net)

  - Establish situational awareness communications thru monitoring of key frequencies/networks (review WA SCIP, ESF2 appndx1 & NIFOG for possible channels to monitor)

  - Establish Public Awareness communications capability in concert with JIC/PIO (determine operability of KQM & KONP and repair needs to make operable).

  - Establish Communication capabilities in support of Logistics and Resources (i.e. Staging Areas, Mutual Aid, Sheltering, etc. )

- Plan for continuing operations. Expect extended disruption of infrastructure (power grid, Cell sites, internet, fuel shortages etc). Plan logistical support to generator power, portable repeaters, mobile cell sites, ARES operators & equipment (i.e. fuel) etc.

- Plan for restoration of damaged infrastructure, Cell sites, phone land lines, microwave shots, cable runs, repeater sites, Dispatch Centers etc.

- Demobilize in accordance with Demob plan, complete required ICS221’s and turn all documentation in to Doc Unit.